## Slide 1: Content Cadence

## Slide 2: 1 Major Theme per Month
4 Posts (Tier 1 Patreons)
  2 Include an Encounter w/ Battle Map (5-8 pts.)
  2 Are Supplemental Content (3-5 pts.)

## Slide 3: 1 Minor Theme per Month
This Theme is Flexible in Terms of Consistency and Content Cadence
Will Average 4-8 pts. Per Month (Tier 1 Patreons)

## Slide 4: 1 Adventure Per Month
Effort may average 8-13 pts. Per Adventure
For Tier 2 Patreons
Will Most Often Tie into the Major Theme

## Slide 5: Voting on Themes
Available to Tier 1 Patreons
  Tier 2 Patreons may have increased voting power
Ranked Choice Voting
  Provide a list of themes/requests and use that to guide upcoming themes
  Will probably be done in the middle of month and last a week
Free For All Requests/Suggestions
  Enough in one direction could lead to a theme
At The Start of Each Month We Announce Next Month’s Theme
  This way people know what’s in development and have something to look forward to if they’re not a fan of the current theme

## Slide 6: Development Time
Ideation to Playtest Ready
  Encounter: 1 Week Avg
  Monsters: 1 Week Avg.
  Spells, Items, & Feats: 1 Week Avg.
  Races: 1-2 Weeks Avg.
  DM Mechanics: 1-3 Weeks Avg.
  Subclass: 2-3 Weeks Avg.
Document Completion: ½-1 Week Avg.
Buffer Before Release: 2 Weeks
Time Needed to Playtest
  Monsters/Encounters: 1-3 Weeks
  DM Mechanics: 2-4 Weeks
  Spells & Items: 2-4 Weeks
  Subclasses, Races, & Feats: 4+ Weeks

## Slide 7: Development Pipeline (Major Themes)
Month 1
  Poll for desired themes (1 Week)
  Determine content schedule for month after next (1 Week)
  Begin initial development on content
  The timing of this is flexible and may depend on development needs
Month 2
  Announce content for next month
  Complete development on next month’s content
  Begin playtesting content as it is developed
  Begin preparing content documents for release
Month 3
  Begin releasing content across the month
  Complete playtesting and document creation

## Slide 8: Development Pipeline (Minor Themes)
Not As Rigid as the Major Theme
Could Follow the Same Cadence as the Major Theme and Represent a Second Favorite Pick in the Poll
Could Be Something We Already Have Ready and Feel Like Sharing
Could Be the Top Pick in a Poll if the Topic Wasn’t Large Enough to Fill Out a Major Theme
Could Be Left Over Content That Didn’t Fit into a Previous Theme
Could Be Odd Ball Content That Doesn’t Fit Neatly into a Normal Content Cadence

## Slide 9: Public Benefits
All Player Option Posts (Subclasses, Races, Spells, Feats)
Most Monsters
  Exceptions might include things like NPCs
Most Monster Compendiums
  This is due to their reliance on WotC art to be fully functional
  Exceptions would be monster compendiums not reliant on art, such as NPCs
Any Subclass or Race Compendiums We Make
DM Mechanics Without Any Extra Bells or Whistles
Random Content Used to Advertise the Patreon

## Slide 10: Tier 1 ($3.00) Benefits
All Creature, Item, & DM Mechanic Posts
All Compendiums
2 Encounters Per Month
Access to the Discord
The Ability to Vote on Themes

## Slide 11: Tier 2 ($5.00) Benefits
1 Adventure per Month
Tentatively: Greater Voting Power on Themes
Tentatively: More In Depth Lore and Adventure Hooks
Tentatively: Loot Tables for Creatures

## Slide 12: Tier 3 ($?.00) Benefits
VTT Content
Credits On All Documents